## Payment Claim
Payment Claim
Progress Certificate No. |  | PC004
Payment Period |  | 06/12/25 - 31/01/25
Contractor Representative |  | Gavin Law
Contractor Name |  | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
PO No. |  | 3106883069
SAP WBS |  | Z-2264070.04.50.30.01
Contract No. |  | PH-AA-0001
Contract Title |  | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
AUD
Claim Value |  | 0
Amount Approved for Payment |  | 174764.75 |  |  | 174764.75
AUSTRALIAN DOLLAR
1 | CONTRACT PRICE (excl. GST) |  |  | 2316587.15
2 | AUTHORISED VARIATIONS |  |  | 599324.9
3 | REVISED CONTRACT PRICE |  |  | 2915912.05
4 | APPROVED TO DATE |  |  | 1329178.48 | TRUE
| PC001 Sep-25 |  |  | 41059.03
| PC002 Oct-25 |  |  | 652005.36
| PC003 Nov-25 - 6 Dec-25 |  |  | 461349.34
| PC004 Dec 25 - Jan 26 |  |  | 174764.75
5 | REMAINING VALUE |  |  | 1586733.57
In accordance with General Condition cl 14.2(c), the Company Representative responds with reasons for withholding payment as follows:
- Refer to comments included at Attachment A
Company Notes:
Pump charges have been removed from this Progress Claim. WM will review with RAC which pumps are on site and charges can be captured in PC004.
Attachments:
1 - PC003
Approval |  | Name | Signature | Date
Procurement and Contracts |  | Jake Shaw
Project Controls |  | Tong Fu
Project Controls |  | Alfredo Vitangcol
Project Manager |  | Shaine Sayed
Attachment A - PC003

## Payment_Summary
PAYMENT CLAIM
Contract Ref: | PH-AA-0001
Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
SAP WBS: | Z-2264070.04.50.30.01
Payment No: | PC004
Payment Period: | 06/12/25 - 31/01/25
[18 empty] | SUBMITTED BY CONTRACTOR | [5 empty] | ASSESSED BY COMPANY | [5 empty] | DELTA THIS CLAIM
|  |  |  | Awarded Contract Price |  | Contract Variation 001 |  | Contract Variation 002 |  | Contract Variation 003 |  | Contract Variation 004 |  | Contract Variation 00 |  | Revised Contract Price |  | This Claim |  | Previously Certified Amounts |  | Cumulative to Date |  | This Claim |  | Previously Certified Amounts |  | Cumulative to Date
ITEM | DESCRIPTION | LS/CP/ SOR/PS | UNIT | Hours | Amount (AUD) | Hours | Amount (AUD) | Hours | Amount (AUD) | Hours | Amount (AUD) | Hours | Amount (AUD) | Hours | Amount (AUD) | Hours | Amount (AUD) | QTY | AMOUNT (A) | QTY | AMOUNT (B) | QTY | AMOUNT (C = A + B) | QTY | AMOUNT (D) | QTY | AMOUNT (E) | QTY | AMOUNT (F = D + E) | QTY | AMOUNT (G = F - C)
A.2 | Schedule of Rates |  |  |  | 2316587.15 | [11 empty] | 2867960.05
A.2.1 | Rates for Mobilisation & Demobilisation - Manual Personnel | SOR | Lot | 222 | 35451.9 | 325 | 46562.9 | [8 empty] | 547 | 82014.8 | 0 | 0 | 81 | 25349.85 | 81 | 25349.85 | 0 | 0 | 81 | 25349.85 | 81 | 25349.85 | 0 | 0
A.2.3 | Rates for Labour | SOR | Hours | 6048 | 698544 | 3555 | 504810 | [8 empty] | 9603 | 1203354 | 0 | 0 | 3400.5 | 396110 | 3400.5 | 396110 | 1470 | 174753.75 | 3135 | 365444.75 | 4605 | 540198.5 | 1470 | 174753.75
A.2.4 | Rates for Mobilisation & Demobilisation - Plant & Equipment | SOR | Lot | 0 | 412206.65 | 0 | 0 | [8 empty] | 0 | 412206.65 | 0 | 0 | 9 | 348397.3 | 9 | 348397.3 | 0 | 0 | 9 | 348397.3 | 9 | 348397.3 | 0 | 0
A.2.5 | Rates for Plant & Equipment | SOR | Days | 0 | 1170384.6 | 0 | 0 | [8 empty] | 0 | 1170384.6 | 0 | 0 | 3779.5 | 354159.63 | 3779.5 | 354159.63 | 9.1 | 11 | 100.7 | 83 | 109.8 | 94 | 9.1 | 11
A.4 | Variations
A.4.1 | Variations - Site Instruction | CP | Lot |  |  | 0 | 47952 | [8 empty] | 0 | 47952 | 0 | 0 | 0 | 30396.95 | 0 | 30396.95 | 0 | 0 | 0 | 30396.95 | 0 | 30396.95 | 0 | 0
| Total |  |  | 6270 | 2316587.15 |  | 599324.9 |  | 0 |  | 0 |  | 0 |  | 0 | 10150 | 2915912.05 | 0 | 0 | 7270 | 1154413.73 | 7270 | 1154413.73 | 1479.1 | 174764.75 | 3325.7 | 769671.85 | 4804.8 | 944436.6 | 1479.1 | 174764.75

## A.2.1_Mob&Demob Personnel
Contract Ref: | PH-AA-0001
Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
SAP WBS: | Z-2264070.04.50.30.01
Payment No: | PC004
Payment Period: | 06/12/25 - 31/01/25
TABLE A.2.1 - Mobilisation / Demobilistation - Personnel
[11 empty] | Hours (Previous Payments) | [9 empty] | Payments (AUD) (Previous Payments)
Item | Position | Personnel Name(s) | Labour Rate AUD/Hr | UoM | This Payment | Previous Payments Hours | Total Payment Hours | This Payment AUD | Previous Payments AUD | Total Payment AUD | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | Contractor Comments | Company Comments
Mobilisation - Personnel
A.2.1-101a | Operators - pre-mobilisation medical | Byron McCann | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC001: 4 | 462 | [10 empty] | 4hrs as per Schedule A.99
A.2.1-101a | Operators - pre-mobilisation medical | Steven Mungatopi | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC001: 4 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Arthur De Saint Andrieu | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC001: 4 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Andres Ramirez | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC001: 4 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Jack Barlee | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC001: 4 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Stewart Rioli | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC002: 4 | 0 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Joy Mather | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC002: 4 | 0 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Payden Coghill | 115.5 | Hrs |  | 4 | 4 | 0 | 462 | 462 | Hours (Previous Payments) PC002: 4 | 0 | 462
A.2.1-101a | Operators - pre-mobilisation medical | Jarrad Ernst | 142 | Hrs |  | 4 | 4 | 0 | 568 | 568 | Hours (Previous Payments) PC003: 4 |  |  | 568
| Subtotal - pre-mobilisation medical |  |  |  | 0 | 36 | 36 | 0 | 4264 | 4264 | 20 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mobilisation - preparation & onboarding
A.2.1-101b | Operators - preparation & onboarding | Byron McCann | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 1750.65 | [10 empty] | incl's site-specific PPE, (2hrs + 3hrs) for offsite / onsite inductions as per Schedule A.99 | bar: Hours (Previous Payments) PC001
A.2.1-101b | Operators - preparation & onboarding | Steven Mungatopi | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 1750.65 | bar: Hours (Previous Payments) PC001
A.2.1-101b | Operators - preparation & onboarding | Arthur De Saint Andrieu | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 1750.65 | bar: Hours (Previous Payments) PC001
A.2.1-101b | Operators - preparation & onboarding | Andres Ramirez | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 1750.65 | bar: Hours (Previous Payments) PC001
A.2.1-101b | Operators - preparation & onboarding | Jack Barlee | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 1750.65 | bar: Hours (Previous Payments) PC001
A.2.1-101b | Operators - preparation & onboarding | Stewart Rioli | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 0 | 1750.65 | bar: Hours (Previous Payments) PC002
A.2.1-101b | Operators - preparation & onboarding | Joy Mather | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 0 | 1750.65 | bar: Hours (Previous Payments) PC002
A.2.1-101b | Operators - preparation & onboarding | Payden Coghill | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [10 empty] | 0 | 1750.65 | bar: Hours (Previous Payments) PC002
A.2.1-101b | Operators - preparation & onboarding | Jarrad Ernst | 1750.65 | EA |  | 1 | 1 | 0 | 1750.65 | 1750.65 | [12 empty] | 1750.65 | bar: Hours (Previous Payments) PC003
| Subtotal - preparation & onboarding |  |  |  | 0 | 9 | 9 | 0 | 15755.85 | 15755.85 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mobilisation - mobilise to site
A.2.1-101c | Operators - mobilise to site | Byron McCann | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC001: 5 | 577.5 | [10 empty] | 5hrs travel time as per Schedule A.99
A.2.1-101c | Operators - mobilise to site | Steven Mungatopi | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC001: 5 | 577.5
A.2.1-101c | Operators - mobilise to site | Arthur De Saint Andrieu | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC001: 5 | 577.5
A.2.1-101c | Operators - mobilise to site | Andres Ramirez | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC001: 5 | 577.5
A.2.1-101c | Operators - mobilise to site | Jack Barlee | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC001: 5 | 577.5
A.2.1-101c | Operators - mobilise to site | Stewart Rioli | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC002: 5 |  | 577.5
A.2.1-101c | Operators - mobilise to site | Joy Mather | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC002: 5 |  | 577.5
A.2.1-101c | Operators - mobilise to site | Payden Coghill | 115.5 | Hrs |  | 5 | 5 | 0 | 577.5 | 577.5 | Hours (Previous Payments) PC002: 5 |  | 577.5
A.2.1-101c | Operators - mobilise to site | Jarrad Ernst | 142 | Hrs |  | 5 | 5 | 0 | 710 | 710 | Hours (Previous Payments) PC003: 5 |  |  | 710
| Subtotal - mobilise to site |  |  |  | 0 | 45 | 45 | 0 | 5330 | 5330 | 25 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Demobilisation - Personnel
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
A.2.1-301a | Operators - demobilise from site |  | 115.5 | Hrs |  | 0 | 0 | 0 | 0 | 0
| Subtotal - mobilise to site |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| Total - Mobilisation / Demobilistation - Personnel |  |  |  | 0 | 81 | 81 | 0 | 25349.85 | 25349.85 | 45 | 27 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13950.75 | 8370.45 | 3028.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## A.2.3 Labour Costs
| Contract Ref: | PH-AA-0001
| Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
| Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
| SAP WBS: | Z-2264070.04.50.30.01
| Payment No: | PC004
| Payment Period: | 06/12/25 - 31/01/25
Table A.2.3 - Costs for Personnel
| Item | Position | Personnel Name(s) | Labour Rate AUD/Hr | [57 empty] | This Payment Hours | Previous Payments Hours | Total Payment Hours | This Payment AUD | Previous Payments AUD | Total Payment AUD | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | Contractor Comments | Company Comments | time axis 2025-12-06 to 2026-01-31
See comments in individual cells
| A.2.3-101 | Operators | Byron McCann | 115.5 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11.5; 2026-01-07: 11.5; 2026-01-08: 11.5; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5; 2026-01-18: 10 | 241 | 587 | 828 | 27835.5 | 67798.5 | 95634 | 16 | 269.5 | 301.5 | [7 empty] | 1848 | 31127.25 | 34823.25
| A.2.3-101 | Operators | Steven Mungatopi | 115.5 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11.5; 2026-01-07: 11.5; 2026-01-08: 11.5; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5; 2026-01-18: 10 | 229.5 | 535.5 | 765 | 26507.25 | 61850.25 | 88357.5 | 16 | 228 | 291.5 | [7 empty] | 1848 | 26334 | 33668.25
| A.2.3-101 | Operators | Arthur De Saint Andrieu | 115.5 | 2025-12-07: 0; 2025-12-08: 0; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11.5; 2026-01-07: 11.5; 2026-01-08: 11.5; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5; 2026-01-18: 10 | 211 | 587 | 798 | 24370.5 | 67798.5 | 92169 | 16 | 269.5 | 301.5 | [7 empty] | 1848 | 31127.25 | 34823.25
| A.2.3-101 | Operators | Jack Barlee | 115.5 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11.5; 2026-01-07: 11.5; 2026-01-08: 11.5; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5 | 231 | 587 | 818 | 26680.5 | 67798.5 | 94479 | 16 | 269.5 | 301.5 | [7 empty] | 1848 | 31127.25 | 34823.25
| A.2.3-101 | Operators | Stewart Rioli | 115.5 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-12: 10; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5; 2026-01-18: 10 | 163.5 | 505.5 | 669 | 18884.25 | 58385.25 | 77269.5 |  | 204 | 301.5 | [8 empty] | 23562 | 34823.25
10 | A.2.3-101 | Operators | Payden Coghill | 115.5 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-08: 10; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 11.5; 2026-01-14: 11.5; 2026-01-15: 11.5; 2026-01-16: 11.5; 2026-01-17: 11.5; 2026-01-18: 10 | 206.5 | 206.5 | 413 | 23850.75 | 23850.75 | 47701.5 |  | 0 | 206.5 | [8 empty] | 0 | 23850.75
| A.2.3-101 | Operators | Jarrad Ernst | 142 | 2025-12-07: 11.5; 2025-12-08: 11.5; 2025-12-09: 11.5; 2025-12-10: 11.5; 2025-12-11: 11.5; 2025-12-12: 11.5; 2025-12-13: 11.5; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11.5; 2026-01-07: 11.5; 2026-01-08: 11.5; 2026-01-09: 11.5; 2026-01-10: 11.5; 2026-01-11: 11.5; 2026-01-12: 11.5; 2026-01-13: 6.5 | 187.5 | 126.5 | 314 | 26625 | 17963 | 44588 |  | 0 | 126.5 | [8 empty] | 0 | 17963
|  |  | TOTAL |  | 0 | 61.5 | 61.5 | 61.5 | 80.5 | 80.5 | 80.5 | 69 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 57.5 | 57.5 | 67.5 | [9 empty] | 50 | [12 empty] | 0 | 1470 | 3135 | 4605 | 174753.75 | 365444.75 | 540198.5 | 64 | 1240.5 | 1830.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7392 | 143277.75 | 214775 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## A.2.4_Mob&Demob PE
Contract Ref: | PH-AA-0001
Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
SAP WBS: | Z-2264070.04.50.30.01
Payment No: | PC004
Payment Period: | 06/12/25 - 31/01/25
Table A.2.4 - Mobilisation & Demobilisation - Plant & Equipment
[11 empty] | Hours (Previous Payments) | [9 empty] | Payments (AUD) (Previous Payments)
Item | Equipment Type | Equipment No. | Rate (AUD) | UoM | This Payment | Previous Payments Hours | Total Payment Hours | This Payment AUD | Previous Payments AUD | Total Payment AUD | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | Contractor Comments | Company Comments
Mobilisation - Plant and Equipment (by road)
A.7.4-101 | 25t Excavator LGP Tracks | EX10 | 71393.85 | Lot |  | 1 | 1 | 0 | 71393.85 | 71393.85 | [11 empty] | 71393.85 | bar: Hours (Previous Payments) PC002
A.7.4-102 | 36t Excavator LGP Tracks | EX17 | 78376.65 | Lot |  | 1 | 1 | 0 | 78376.65 | 78376.65 | [11 empty] | 78376.65 | bar: Hours (Previous Payments) PC002
A.7.4-103 | D6 Dozer LGP Tracks | YQ087 | 47512.3 | Lot |  | 1 | 1 | 0 | 47512.3 | 47512.3 | [11 empty] | 47512.3 | bar: Hours (Previous Payments) PC002
A.7.4-104a | 30t Articulated Dumptruck #1 | TAT52 | 33811.8 | Lot |  | 1 | 1 | 0 | 33811.8 | 33811.8 | [11 empty] | 33811.8 | bar: Hours (Previous Payments) PC002
A.7.4-104b | 30t Articulated Dumptruck #2 | TAT56 | 33811.8 | Lot |  | 1 | 1 | 0 | 33811.8 | 33811.8 | [11 empty] | 33811.8 | bar: Hours (Previous Payments) PC002
A.7.4-105 | Service Truck | IGROUP58 | 35967.25 | Lot |  | 1 | 1 | 0 | 35967.25 | 35967.25 | [11 empty] | 35967.25 | bar: Hours (Previous Payments) PC002
A.7.4-106 | Rigid Watercart | TW06 | 27874.55 | Lot |  | 1 | 1 | 0 | 27874.55 | 27874.55 | [11 empty] | 27874.55 | bar: Hours (Previous Payments) PC002
A.7.4-107a | 4WD Twin Cab LV #1 | CC21IT | 9824.55 | Lot |  | 1 | 1 | 0 | 9824.55 | 9824.55 | [11 empty] | 9824.55 | bar: Hours (Previous Payments) PC002
A.7.4-107b | 4WD Twin Cab LV #2 | CC95AY | 9824.55 | Lot |  | 1 | 1 | 0 | 9824.55 | 9824.55 | [11 empty] | 9824.55 | bar: Hours (Previous Payments) PC002
| Subtotal - Plant and Equipment (by road) |  |  |  | 0 | 9 | 9 | 0 | 348397.3 | 348397.3 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348397.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Demobilisation - Plant and Equipment (by barge)
A.7.4-101 | 25t Excavator LGP Tracks |  | 6790.85 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-102 | 36t Excavator LGP Tracks |  | 8044.85 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-103 | D6 Dozer LGP Tracks |  | 13294.6 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-104a | 30t Articulated Dumptruck #1 |  | 10552.3 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-104b | 30t Articulated Dumptruck #2 |  | 10552.3 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-105 | Service Truck |  | 6386.05 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-106 | Rigid Watercart |  | 4819.1 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-107a | 4WD Twin Cab LV #1 |  | 1684.65 | Lot |  | 0 | 0 | 0 | 0 | 0
A.7.4-107b | 4WD Twin Cab LV #2 |  | 1684.65 | Lot
| Subtotal - Plant and Equipment (by barge) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total - Mobilisation & Demobilisation - Plant & Equipment |  |  |  | 0 | 9 | 9 | 0 | 348397.3 | 348397.3 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348397.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## A.2.5 PE
Contract Ref: | PH-AA-0001
Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
SAP WBS: | Z-2264070.04.50.30.01
Payment No: | PC004
Payment Period: | 06/12/25 - 31/01/25
Table A.2.5 - Costs for Plant and Equipment
Item | Plant Classification | Plant Equipment Reg. No | PE Rate AUD/Day | PE Rate AUD/Hr | [45 empty] | Hours as per signed Dayworks | Combined monthly hours | Previous Payments Hours | Total Payment Hours | This Payment AUD | Previous Payments AUD | Total Payment AUD | PC001 | PC002 | PC003 | PC004 | PC005 | PC006 | PC007 | PC008 | PC009 | PC010 | Hours as per signed Dayworks | Combined monthly hours | Previous Payments Hours | Total Payment Hours | 0 | This Payment AUD | Previous Payments AUD | Total Payment AUD | 0 | PC001 | Contractor Comments | Company Comments | time axis 2025-12-06 to 2026-01-31
A.7.4-101 | 25t Excavator LGP Tracks | EX10 | 1530.65 | 139.15 | 2025-12-07: 6; 2025-12-08: 4; 2025-12-09: 7; 2025-12-10: 6; 2025-12-11: 8; 2025-12-12: 8; 2025-12-13: 8; 2026-01-06: 7; 2026-01-07: 6; 2026-01-08: 5; 2026-01-12: 4; 2026-01-13: 8; 2026-01-14: 6; 2026-01-15: 8; 2026-01-16: 8; 2026-01-17: 3; 2026-01-18: 2 | 65 | 11 | #VALUE! | 10 | 556.6 | 148 | 5 |  | 88 | 148 | [8 empty] | 12245.2 | 20594.2 | [8 empty] | See comments in individual cells
| 25t Excavator LGP Tracks - Standby |  | 919.6 | 83.6 | 2025-12-07: 4; 2025-12-08: 6; 2025-12-09: 3; 2025-12-10: 5; 2025-12-11: 3; 2025-12-12: 3; 2025-12-13: 3; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 4; 2026-01-07: 5; 2026-01-08: 6; 2026-01-12: 7; 2026-01-13: 3; 2026-01-14: 5; 2026-01-15: 3; 2026-01-16: 3; 2026-01-17: 8; 2026-01-18: 9 | 62 |  | #VALUE! | 12 | 585.2 | 113.5 | 17 |  | 76 | 113.5 | [8 empty] | 6353.6 | 9488.6
| 25t Excavator LGP Tracks - Breakdown |  | 0 | 0 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 29 | 0 |  |  | 29 | [9 empty] | 0
A.7.4-102 | 36t Excavator LGP Tracks | EX17 | 1851.3 | 168.3 | 2025-12-07: 7; 2025-12-08: 5; 2025-12-09: 7; 2025-12-10: 8; 2025-12-11: 8; 2025-12-12: 8; 2025-12-13: 5; 2026-01-09: 3; 2026-01-10: 5; 2026-01-11: 7; 2026-01-12: 3; 2026-01-13: 6; 2026-01-14: 8; 2026-01-15: 5; 2026-01-16: 5; 2026-01-17: 3; 2026-01-18: 2 | 63 | 11 | #VALUE! | 11 | 504.9 | 160 | 5 |  | 22 | 160 | [8 empty] | 3702.6 | 26928
| 36t Excavator LGP Tracks - Standby |  | 1113.2 | 101.2 | 2025-12-07: 3; 2025-12-08: 5; 2025-12-09: 3; 2025-12-10: 3; 2025-12-11: 3; 2025-12-12: 3; 2025-12-13: 6; 2025-12-14: 10; 2026-01-09: 7; 2026-01-10: 5; 2026-01-11: 4; 2026-01-12: 8; 2026-01-13: 5; 2026-01-14: 3; 2026-01-15: 6; 2026-01-16: 6; 2026-01-17: 8; 2026-01-18: 9 | 52 |  | #VALUE! | 11 | 809.6 | 130.5 | 17 |  | 25 | 130.5 | [8 empty] | 2530 | 13206.6
| 36t Excavator LGP Tracks - Breakdown |  | 0 | 0 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 0 | 0 |  | 8 | 0 | [8 empty] | 0 | 0
A.7.4-103 | D6 Dozer LGP Tracks | YQ087 | 2813.25 | 255.75 | 2025-12-07: 2.4; 2025-12-08: 3; 2025-12-09: 3; 2025-12-10: 8.1; 2026-01-11: 5.3; 2026-01-12: 4.1; 2026-01-13: 5.9; 2026-01-14: 1.7; 2026-01-15: 7; 2026-01-16: 1.6 | 21.8 | 11 | #VALUE! | 5.8 | 1048.575 | 107.6 | 0 |  | 52.3 | 107.6 | [8 empty] | 13375.725 | 27518.7
| D6 Dozer LGP Tracks - Standby |  | 1687.95 | 153.45 | 2025-12-07: 8.6; 2025-12-08: 7; 2025-12-09: 7; 2025-12-10: 2.9; 2026-01-10: 11; 2026-01-11: 5.7; 2026-01-12: 6.9; 2026-01-13: 5.1; 2026-01-15: 4; 2026-01-16: 9.4 | 42.2 |  | #VALUE! | 6.9 | 1058.805 | 182.9 | 0 |  | 112.7 | 182.9 | [8 empty] | 17293.815 | 28066.005
A.7.4-104a | 30t Articulated Dumptruck #1 | TAT52 | 1972.3 | 179.3 | 2025-12-08: 0; 2025-12-10: 5.2; 2025-12-11: 7.3; 2025-12-12: 8.3; 2025-12-13: 4; 2026-01-08: 2.3; 2026-01-09: 4.3; 2026-01-10: 3.7; 2026-01-11: 2.5; 2026-01-13: 3.4; 2026-01-14: 5.8; 2026-01-15: 5.8; 2026-01-16: 8; 2026-01-17: 2.8; 2026-01-18: 2.2 | 37.6 | 11 | #VALUE! | 5.8 | 0 | 148.9 | 5 |  | 65.6 | 148.9 | [8 empty] | 11762.08 | 26697.77
| 30t Articulated Dumptruck #1 - Standby |  | 1185.8 | 107.8 | 2025-12-10: 5.8; 2025-12-11: 3.7; 2025-12-12: 3.7; 2025-12-13: 7; 2025-12-14: 10; 2026-01-08: 8.7; 2026-01-09: 5.7; 2026-01-10: 6.3; 2026-01-11: 8.5; 2026-01-13: 7.6; 2026-01-14: 5.2; 2026-01-15: 5.2; 2026-01-16: 3; 2026-01-17: 8.2; 2026-01-18: 8.8 | 59.4 |  | #VALUE! | 5.2 | 0 | 71.9 | 17 |  | 88.4 | 71.9 | [8 empty] | 9529.52 | 7750.82
| 30t Articulated Dumptruck #1 - Breakdown |  | 0 | 0 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2026-01-12: 11 | 30 |  | #VALUE! | 11 | 0 | 69.7 | 0 |  | 11 | 69.7 | [8 empty] | 0 | 0
A.7.4-104b | 30t Articulated Dumptruck #2 | TAT56 | 1972.3 | 179.3 | 2025-12-10: 6; 2025-12-11: 6; 2025-12-12: 7; 2026-01-08: 3.5; 2026-01-09: 5; 2026-01-10: 5; 2026-01-11: 1; 2026-01-13: 4; 2026-01-14: 4; 2026-01-15: 5.8; 2026-01-16: 7.2; 2026-01-17: 1.5 | 33.5 | 11 | #VALUE! | 4 | 0 | 3.3 | 1.5 |  | 22.5 | 3.3 | [8 empty] | 4034.25 | 591.69
| 30t Articulated Dumptruck #2 - Standby |  | 1185.8 | 107.8 | 2025-12-10: 5; 2025-12-11: 5; 2025-12-12: 4; 2025-12-13: 11; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11; 2026-01-07: 11; 2026-01-08: 6.5; 2026-01-09: 5; 2026-01-10: 5; 2026-01-11: 9; 2026-01-13: 5; 2026-01-14: 5; 2026-01-15: 5; 2026-01-16: 3.8; 2026-01-17: 9.5; 2026-01-18: 11 | 92.5 |  | #VALUE! | 5 | 0 | 0 | 20.5 |  | 0 | 0 | [8 empty] | 0 | 0
| 30t Articulated Dumptruck #2 - Breakdown |  | 0 | 0 | 2025-12-07: 10; 2025-12-08: 10; 2025-12-09: 10; 2026-01-12: 11; 2026-01-13: 2; 2026-01-14: 2 | 30 |  | #VALUE! | 13 | 0 | 287.2 | 0 |  | 119.5 | 287.2 | [8 empty] | 0 | 0
A.7.4-105 | Service Truck | IGROUP58 | 1911.8 | 173.8 | 2025-12-07: 3.5; 2025-12-08: 0; 2025-12-09: 0.4; 2025-12-10: 0.4; 2025-12-11: 0.5; 2026-01-06: 6.1; 2026-01-07: 5.4; 2026-01-08: 1; 2026-01-09: 1.8; 2026-01-10: 3; 2026-01-11: 4.8; 2026-01-12: 6.8; 2026-01-13: 1; 2026-01-14: 0.2; 2026-01-15: 0.4; 2026-01-16: 0.5 | 26.9 | 11 | #VALUE! | 7 | 1181.84 | 47.6 | 0 |  | 14 | 47.6 | [8 empty] | 2433.2 | 8272.88
| Service Truck - Standby |  | 1149.5 | 104.5 | 2025-12-07: 6.5; 2025-12-08: 10; 2025-12-09: 9.6; 2025-12-10: 10.6; 2025-12-11: 10.6; 2025-12-12: 11; 2025-12-13: 11; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 4.9; 2026-01-07: 5.6; 2026-01-08: 10; 2026-01-09: 8.2; 2026-01-10: 7; 2026-01-11: 6.2; 2026-01-12: 4.2; 2026-01-13: 10; 2026-01-14: 10.8; 2026-01-15: 10.6; 2026-01-16: 10.5; 2026-01-17: 11; 2026-01-18: 11 | 131.2 |  | #VALUE! | 15 | 438.9 | 228.3 | 22 |  | 151 | 228.3 | [8 empty] | 15779.5 | 23857.35
| Service Truck - Breakdown |  | 0 | 0 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 14.6 | 0 |  |  | 14.6 | [9 empty] | 0
A.7.4-106 | Rigid Watercart | TW06 | 1240.25 | 112.75 | 2025-12-09: 2; 2025-12-10: 2; 2025-12-11: 5; 2025-12-12: 8; 2025-12-13: 8; 2026-01-08: 5; 2026-01-11: 1; 2026-01-14: 3; 2026-01-15: 8; 2026-01-17: 2 | 31 | 11 | #VALUE! | 3 | 0 | 183 | 2 |  | 62 | 183 | [8 empty] | 6990.5 | 20633.25
| Rigid Watercart - Standby |  | 744.15 | 67.65 | 2025-12-09: 8; 2025-12-10: 9; 2025-12-11: 6; 2025-12-12: 3; 2025-12-13: 3; 2025-12-14: 10; 2026-01-05: 10; 2026-01-06: 11; 2026-01-07: 11; 2026-01-08: 6; 2026-01-09: 10; 2026-01-10: 10; 2026-01-11: 9; 2026-01-13: 11; 2026-01-14: 8; 2026-01-15: 3; 2026-01-16: 11; 2026-01-17: 9; 2026-01-18: 11 | 106 |  | #VALUE! | 8 | 0 | 95.5 | 20 |  | 102 | 95.5 | [8 empty] | 6900.3 | 6460.575
| Rigid Watercart - Breakdown |  | 0 | 0 | 2025-12-07: 10; 2025-12-08: 10; 2026-01-12: 11 | 20 |  | #VALUE! | 11 | 0 | 12 | 0 |  |  | 12 | [9 empty] | 0
A.7.4-107a | 4WD Twin Cab LV #1 | CC21IT | 320.65 | 29.15 | 2025-12-07: 11; 2025-12-08: 11; 2025-12-09: 11; 2025-12-10: 11; 2025-12-11: 11; 2025-12-12: 11; 2025-12-13: 11; 2025-12-14: 11; 2026-01-05: 11; 2026-01-06: 11; 2026-01-07: 11; 2026-01-08: 11; 2026-01-09: 11; 2026-01-10: 11; 2026-01-11: 11; 2026-01-12: 11; 2026-01-13: 11; 2026-01-14: 11; 2026-01-15: 11; 2026-01-16: 11; 2026-01-17: 11; 2026-01-18: 11 | 165 | 11 | #VALUE! | 22 | 320.65 | 297 | 22 |  | 0 | 297 | [8 empty] | 0 | 8657.55
| 4WD Twin Cab LV #1 - Standby |  | 193.6 | 17.6 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0
A.7.4-107b | 4WD Twin Cab LV #2 | CC95AY | 320.65 | 29.15 | 2025-12-07: 11; 2025-12-08: 11; 2025-12-09: 11; 2025-12-10: 11; 2025-12-11: 11; 2025-12-12: 11; 2025-12-13: 11; 2025-12-14: 11; 2026-01-05: 11; 2026-01-06: 11; 2026-01-07: 11; 2026-01-08: 11; 2026-01-09: 11; 2026-01-10: 11; 2026-01-11: 11; 2026-01-12: 11; 2026-01-13: 11; 2026-01-14: 11; 2026-01-15: 11; 2026-01-16: 11; 2026-01-17: 11; 2026-01-18: 11 | 165 | 11 | #VALUE! | 22 | 320.65 | 297 | 22 |  | 0 | 297 | [8 empty] | 0 | 8657.55
| 4WD Twin Cab LV #2 - Standby |  | 193.6 | 17.6 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 0 | 0 |  | 0 | 0 | [8 empty] | 0 | 0
A.7.4-107b | 4WD Twin Cab LV #3 | TBA | 320.65 | 29.15 | 2025-12-07: 11; 2025-12-08: 11; 2025-12-09: 11; 2025-12-10: 11; 2025-12-11: 11; 2025-12-12: 11; 2025-12-13: 11; 2025-12-14: 11; 2026-01-05: 11; 2026-01-06: 11; 2026-01-07: 11; 2026-01-08: 11; 2026-01-09: 11; 2026-01-10: 11; 2026-01-11: 11; 2026-01-12: 11; 2026-01-13: 11; 2026-01-14: 11; 2026-01-15: 11; 2026-01-16: 11; 2026-01-17: 11; 2026-01-18: 11 | 165 | 11 | #VALUE! | 22 | 320.65 | 132 | 22 |  |  | 132 | [9 empty] | 3847.8
| 4WD Twin Cab LV #3 - Standby |  | 193.6 | 17.6 | [45 empty] | 0 |  | #VALUE! | 0 | 0 | 0 | 0 |  |  | 0 | [9 empty] | 0
|  | TOTAL |  |  | 0 | 104 | 103 | 103 | 110 | 99.1 | 100 | 99 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 77 | 77 | 87 | 83 | 94 | 97 | 110 | 110 | 100.7 | 109.8 | 110 | 99 | 83 | 94 | 110 | 110 | 100.7 | 109.8 | 99 | 99 | 0 | 1399.1 | 110 | #VALUE! | 210.7 | 0 | 7146.37 | 2759.5 | 198 | 0 | 0 | 2759.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## A.4_Purchase
Contract Ref: | PH-AA-0001
Contract Title: | PLANT HIRE SERVICES FOR BENTHIC REMOVAL
Contractor: | Rirratjingu Enterprises Pty Ltd (ACN 56 639 548 137)
SAP WBS: | Z-2264070.04.50.30.01
Payment No: | PC004
Payment Period: | 06/12/25 - 31/01/25
Table A.4 - Purchase
Payment No | Item No. | Description | Invoice Date | Invoice No. | Vendor Name | Invoice Amount (AUD) Excl. GST | Markup (12%) | Total | Contractor Comments | Company Comments
PC001 | A.4 | Site Instruction 001 - Signage | Various | Various | Various | 15953.82 | 1914.4584 | 17868.2784
PC002 | A.4 | Site Instruction 002 Float moves | 2025-11-07 | Docket no. 41301 | BCC | 1800 | 216 | 2016
PC002 | A.4 | Wallaby Beach Accomodation |  | 1787 | East Arnhem Real Estate | 7318.14 | 878.1768 | 8196.3168
PC003 | A.4 | Wallaby Beach Accomodation - Jarrad Ernst | 2025-12-03 | 2035 | East Arnhem Real Estate | 2068.17 | 248.1804 | 2316.3504
PC004 | A.4
PC004 | A.4
PC004 | A.4
PC004 | A.4
|  | Subtotal for This Payment |  |  | PC004 | 0 | 0 | 0
.
|  | Total - Cumulative |  |  |  | 27140.13 | 3256.82 | 30396.95

## Monthly Claim (Client)
Monthly Claim - Rio Tinto
Month Start (enter first of month): | 2025-11-01 | [8 empty] | Minimum hours per calendar month | 200
Month End (auto): | 2025-12-06
Equipment | Operated Hours | Standby Hours | Total Hours | Plant Rate | Days Hired | Variations Rate | Operator Rate | Standby Rate | Operated ex GST | Standby ex GST | Prep & Onboard | Mob Barge | DeMob Barge | Mob Road | DeMob Road | Op Induction | Op Mob | Op DeMob | Fixed ex GST | Subtotal ex GST | Top-up Hours to Min | Operated Rate (/hr) | Top-up ex GST | Adj total ex GST
25t Excavator LGP Tracks | 151 | 153 | 304 | 139.15 |  |  |  | 83.6 | 21011.65 | 12790.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33802.45 | 0 | 139.15 | 0 | 33802.45
36t Excavator LGP Tracks | 163 | 141 | 304 | 168.3 |  |  |  | 101.2 | 27432.9 | 14269.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41702.1 | 0 | 168.3 | 0 | 41702.1
D6 Dozer LGP Tracks | 104.9 | 190.1 | 295 | 255.75 |  |  |  | 153.45 | 26828.175 | 29170.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55999.02 | 0 | 255.75 | 0 | 55999.02
Bell 30t Articulated Dumptruck #1 | 3.3 | 30 | 33.3 | 179.3 |  |  |  | 107.8 | 591.69 | 3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825.69 | 166.7 | 179.3 | 29889.31 | 7059.69 | Is this formula correct?
Komatsu 30t Articulated Dumptruck #2 | 145.1 | 114.9 | 260 | 179.3 |  |  |  | 107.8 | 26016.43 | 12386.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38402.65 | 0 | 179.3 | 0 | 38402.65
Service Truck | 38.2 | 259.2 | 297.4 | 173.8 |  |  |  | 104.5 | 6639.16 | 27086.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33725.56 | 0 | 173.8 | 0 | 33725.56
Rigid Watercart | 183 | 121 | 304 | 112.75 |  |  |  | 67.65 | 20633.25 | 8185.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28818.9 | 0 | 112.75 | 0 | 28818.9
4WD Twin Cab LV #1 | 308 | 0 | 308 | 29.15 |  |  |  | 17.6 | 8978.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8978.2 | 0 | 29.15 | 0 | 8978.2
4WD Twin Cab LV #2 | 308 | 0 | 308 | 29.15 |  |  |  | 17.6 | 8978.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8978.2 | 0 | 29.15 | 0 | 8978.2
RE 4WD Twin Cab LV #1 | 132 | 0 | 132 | 29.15 |  |  |  | 29.15 | 3847.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847.8 | 0 | 29.15 | 0 | 3847.8
RE 4WD Twin Cab LV #2 | 0 | 0 | 0 | 29.15 |  |  |  | 17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29.15 |  | 0
Operator 1 | 301 | 0 | 301 |  |  |  | 115.5 | 115.5 | 34765.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34765.5 |  | 115.5 |  | 34765.5
Operator 2 | 301 | 0 | 301 |  |  |  | 115.5 | 115.5 | 34765.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34765.5 |  | 115.5 |  | 34765.5
Operator 3 | 301 | 0 | 301 |  |  |  | 115.5 | 115.5 | 34765.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34765.5 |  | 115.5 |  | 34765.5
Operator 4 | 206 | 0 | 206 |  |  |  | 115.5 | 115.5 | 23793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23793 |  | 115.5 |  | 23793
Operator 5 | 301 | 0 | 301 |  |  |  | 115.5 | 115.5 | 34765.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34765.5 |  | 115.5 |  | 34765.5
Operator 6 | 301 | 0 | 301 |  |  |  | 115.5 | 115.5 | 34765.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34765.5 |  | 115.5 |  | 34765.5
Operator 7 | 0 | 0 | 0 |  |  |  | 115.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 115.5 |  | 0
Supervisor | 136.5 | 0 | 136.5 |  |  |  | 142 | 142 | 19383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19383 |  | 142 |  | 19383
3" Flex Drive Trash Pump |  |  |  |  | 34 | 312.4 |  |  | 10621.6 | [10 empty] | 10621.6
4" Transfer Pump |  |  |  |  | 34 | 187 |  |  | 6358 | [10 empty] | 6358
Wallaby Beach Accommodation | [5 empty] | 2316.3504 |  |  | 2316.3504 | [10 empty] | 2316.3504
[6 empty] | 0 |  |  | 0 | [10 empty] | 0
TOTALS | 3384 | 1009.2 | 4393.2 | [5 empty] | 387256.9054 | 107123.115 | [8 empty] | 0 | 494380.0204 |  |  | 29889.31 | 494380.0204
Note on X10: Warwick Mylchreest: Excluded from total due to availability issues.
Note on V16: Warwick Mylchreest: No top up hours applicable.

## Config
Equipment | Hours per Day
25t Excavator LGP Tracks | 11
36t Excavator LGP Tracks
D6 Dozer LGP Tracks
Bell 30t Articulated Dumptruck #1
Komatsu 30t Articulated Dumptruck #2
Service Truck
Rigid Watercart
4WD Twin Cab LV #1
4WD Twin Cab LV #2
RE 4WD Twin Cab LV #1
RE 4WD Twin Cab LV #2
Operator 1
Operator 2
Operator 3
Operator 4
Operator 5
Operator 6
Operator 7
Supervisor
3" Flex Drive Trash Pump
4" Transfer Pump
Wallaby Beach Accommodation
Wallaby Beach Camp
0

## Daily Log
Date | Equipment | Operated Hours | Standby Hours | Breakdown Hours | Variations Rate Days Hired | Mob (Barge) | DeMob (Barge) | Mob (Road) | DeMob (Road) | Prep/Onboard | Op Induction | Op Mob | Op DeMob | Notes
2025-11-01 | Operator 1 | 11.5 | 0 | 0
2025-11-01 | Operator 2 | 11.5 | 0 | 0
2025-11-01 | Operator 3 | 11.5 | 0 | 0
2025-11-01 | Operator 5 | 11.5 | 0 | 0
2025-11-01 | Operator 6 | 11.5 | 0 | 0
2025-11-01 | D6 Dozer LGP Tracks | 7.8 | 3.2 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | 36t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-01 | Komatsu 30t Articulated Dumptruck #2 | 8.9 | 2.1 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | Rigid Watercart | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | Service Truck | 1 | 10 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-01 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-01 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-01 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-01 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-01 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-02 | Operator 1 | 11.5 | 0 | 0
2025-11-02 | Operator 2 | 11.5 | 0 | 0
2025-11-02 | Operator 3 | 11.5 | 0 | 0
2025-11-02 | Operator 5 | 11.5 | 0 | 0
2025-11-02 | Operator 6 | 11.5 | 0 | 0
2025-11-02 | D6 Dozer LGP Tracks | 2.1 | 8.9 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-02 | Komatsu 30t Articulated Dumptruck #2 | 8.5 | 2.5 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | Rigid Watercart | 10 | 1 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | Service Truck | 1 | 10 | 0 | 0 | [8 empty] | Load, Haul & Place Levee Access Road
2025-11-02 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-02 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-02 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-02 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-02 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-03 | Operator 1 | 11.5 | 0 | 0
2025-11-03 | Operator 2 | 11.5 | 0 | 0
2025-11-03 | Operator 3 | 11.5 | 0 | 0
2025-11-03 | Operator 5 | 11.5 | 0 | 0
2025-11-03 | Operator 6 | 11.5 | 0 | 0
2025-11-03 | D6 Dozer LGP Tracks | 0.2 | 10.8 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | 25t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-03 | Komatsu 30t Articulated Dumptruck #2 | 9.1 | 1.9 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | Service Truck | 2 | 9 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-03 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-03 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-03 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-03 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-03 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-04 | Operator 1 | 11.5 | 0 | 0
2025-11-04 | Operator 2 | 11.5 | 0 | 0
2025-11-04 | Operator 3 | 11.5 | 0 | 0
2025-11-04 | Operator 5 | 11.5 | 0 | 0
2025-11-04 | Operator 6 | 11.5 | 0 | 0
2025-11-04 | D6 Dozer LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Standdown
2025-11-04 | 25t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-04 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-04 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-04 | Komatsu 30t Articulated Dumptruck #2 | 8.8 | 2.2 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-04 | Rigid Watercart | 10 | 1 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-04 | Service Truck | 1 | 10 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-04 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-04 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-04 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-04 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-04 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-05 | Operator 1 | 11.5 | 0 | 0
2025-11-05 | Operator 2 | 11.5 | 0 | 0
2025-11-05 | Operator 3 | 11.5 | 0 | 0
2025-11-05 | Operator 5 | 11.5 | 0 | 0
2025-11-05 | Operator 6 | 11.5 | 0 | 0
2025-11-05 | D6 Dozer LGP Tracks | 4.6 | 6.4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | 36t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-05 | Komatsu 30t Articulated Dumptruck #2 | 8.2 | 2.8 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-05 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-05 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-05 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-05 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-05 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-06 | Operator 1 | 11.5 | 0 | 0
2025-11-06 | Operator 2 | 11.5 | 0 | 0
2025-11-06 | Operator 3 | 11.5 | 0 | 0
2025-11-06 | Operator 5 | 11.5 | 0 | 0
2025-11-06 | Operator 6 | 11.5 | 0 | 0
2025-11-06 | D6 Dozer LGP Tracks | 5.5 | 5.5 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-06 | 25t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-06 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Trench, Realign & Backfill Dewatering Pipeline
2025-11-06 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-06 | Komatsu 30t Articulated Dumptruck #2 | 8.9 | 2.1 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-06 | Rigid Watercart | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-06 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-06 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-06 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-06 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-06 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-06 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-07 | Operator 1 | 11.5 | 0 | 0
2025-11-07 | Operator 2 | 11.5 | 0 | 0
2025-11-07 | Operator 3 | 11.5 | 0 | 0
2025-11-07 | Operator 5 | 11.5 | 0 | 0
2025-11-07 | Operator 6 | 11.5 | 0 | 0
2025-11-07 | D6 Dozer LGP Tracks | 6.5 | 4.5 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-07 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-07 | 36t Excavator LGP Tracks | 6 | 5 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-07 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-07 | Komatsu 30t Articulated Dumptruck #2 | 8.7 | 2.3 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-07 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-07 | Service Truck | 1.8 | 9.2 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-07 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-07 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-07 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-07 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-07 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-08 | Operator 1 | 11.5 | 0 | 0
2025-11-08 | Operator 2 | 11.5 | 0 | 0
2025-11-08 | Operator 3 | 11.5 | 0 | 0
2025-11-08 | Operator 5 | 11.5 | 0 | 0
2025-11-08 | Operator 6 | 11.5 | 0 | 0
2025-11-08 | D6 Dozer LGP Tracks | 5.9 | 5.1 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-08 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-08 | 36t Excavator LGP Tracks | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-08 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-08 | Komatsu 30t Articulated Dumptruck #2 | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-08 | Rigid Watercart | 10 | 1 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-08 | Service Truck | 1 | 10 | 0 | 0 | [8 empty] | Load, Haul, Place & Compact Levee Plug
2025-11-08 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-08 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-08 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-08 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-08 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-09 | Operator 1 | 0 | 0 | 0
2025-11-09 | Operator 2 | 0 | 0 | 0
2025-11-09 | Operator 3 | 0 | 0 | 0
2025-11-09 | Operator 5 | 0 | 0 | 0
2025-11-09 | Operator 6 | 0 | 0 | 0
2025-11-09 | D6 Dozer LGP Tracks | 0 | 0 | 0 | 0
2025-11-09 | 25t Excavator LGP Tracks | 0 | 0 | 0 | 0
2025-11-09 | 36t Excavator LGP Tracks | 0 | 0 | 0 | 0
2025-11-09 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 0 | 0
2025-11-09 | Komatsu 30t Articulated Dumptruck #2 | 0 | 0 | 0 | 0
2025-11-09 | Rigid Watercart | 0 | 0 | 0 | 0
2025-11-09 | Service Truck | 0 | 0 | 0 | 0
2025-11-09 | 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-09 | 4WD Twin Cab LV #2 | 0 | 0 | 0 | 0
2025-11-09 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-09 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 0 | [8 empty] | 1
2025-11-09 | 4" Transfer Pump | 0 | 0 | 0 | 0 | [8 empty] | 1
2025-11-10 | Operator 1 | 11.5 | 0 | 0
2025-11-10 | Operator 2 | 11.5 | 0 | 0
2025-11-10 | Operator 3 | 11.5 | 0 | 0
2025-11-10 | Operator 4 | 10 | 0 | 0
2025-11-10 | Operator 5 | 11.5 | 0 | 0
2025-11-10 | Operator 6 | 11.5 | 0 | 0
2025-11-10 | D6 Dozer LGP Tracks | 8.1 | 2.9 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-10 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-10 | 36t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-10 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-10 | Komatsu 30t Articulated Dumptruck #2 | 8.8 | 2.2 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-10 | Rigid Watercart | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-10 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-10 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-10 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-10 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-10 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-10 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-11 | Operator 1 | 11.5 | 0 | 0
2025-11-11 | Operator 2 | 11.5 | 0 | 0
2025-11-11 | Operator 3 | 11.5 | 0 | 0
2025-11-11 | Operator 4 | 10 | 0 | 0
2025-11-11 | Operator 5 | 11.5 | 0 | 0
2025-11-11 | Operator 6 | 11.5 | 0 | 0
2025-11-11 | D6 Dozer LGP Tracks | 2.2 | 8.8 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-11 | 25t Excavator LGP Tracks | 4 | 7 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-11 | 36t Excavator LGP Tracks | 5 | 6 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-11 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-11 | Komatsu 30t Articulated Dumptruck #2 | 5.3 | 5.7 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-11 | Rigid Watercart | 6 | 5 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-11 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-11 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-11 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-11 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-11 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-11 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-12 | Operator 1 | 11.5 | 0 | 0
2025-11-12 | Operator 2 | 11.5 | 0 | 0
2025-11-12 | Operator 3 | 11.5 | 0 | 0
2025-11-12 | Operator 4 | 11.5 | 0 | 0
2025-11-12 | Operator 5 | 11.5 | 0 | 0
2025-11-12 | Operator 6 | 11.5 | 0 | 0
2025-11-12 | D6 Dozer LGP Tracks | 3.9 | 7.1 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-12 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-12 | 36t Excavator LGP Tracks | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-12 | Bell 30t Articulated Dumptruck #1 | 3.3 | 0 | 7.7 | 0 | [8 empty] | Ran for 3.3 hours and still had issues
2025-11-12 | Komatsu 30t Articulated Dumptruck #2 | 4.2 | 6.8 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-12 | Rigid Watercart | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-12 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-12 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-12 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-12 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-12 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-12 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-13 | Operator 1 | 11.5 | 0 | 0
2025-11-13 | Operator 2 | 11.5 | 0 | 0
2025-11-13 | Operator 3 | 11.5 | 0 | 0
2025-11-13 | Operator 4 | 11.5 | 0 | 0
2025-11-13 | Operator 5 | 11.5 | 0 | 0
2025-11-13 | Operator 6 | 11.5 | 0 | 0
2025-11-13 | D6 Dozer LGP Tracks | 2 | 9 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-13 | 25t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-13 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-13 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-13 | Komatsu 30t Articulated Dumptruck #2 | 9.4 | 1.6 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-13 | Rigid Watercart | 9 | 2 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-13 | Service Truck | 1.8 | 9.2 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-13 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-13 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-13 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-13 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-13 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-14 | Operator 1 | 11.5 | 0 | 0
2025-11-14 | Operator 2 | 11.5 | 0 | 0
2025-11-14 | Operator 3 | 11.5 | 0 | 0
2025-11-14 | Operator 4 | 11.5 | 0 | 0
2025-11-14 | Operator 5 | 11.5 | 0 | 0
2025-11-14 | Operator 6 | 11.5 | 0 | 0
2025-11-14 | D6 Dozer LGP Tracks | 4.8 | 6.2 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-14 | 25t Excavator LGP Tracks | 9 | 2 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-14 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-14 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-14 | Komatsu 30t Articulated Dumptruck #2 | 9 | 2 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-14 | Rigid Watercart | 8 | 3 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-14 | Service Truck | 0.2 | 10.8 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-14 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-14 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-14 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-14 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-14 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-15 | Operator 1 | 11.5 | 0 | 0
2025-11-15 | Operator 2 | 11.5 | 0 | 0
2025-11-15 | Operator 3 | 11.5 | 0 | 0
2025-11-15 | Operator 4 | 11.5 | 0 | 0
2025-11-15 | Operator 5 | 11.5 | 0 | 0
2025-11-15 | Operator 6 | 11.5 | 0 | 0
2025-11-15 | D6 Dozer LGP Tracks | 1.7 | 9.3 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-15 | 25t Excavator LGP Tracks | 9 | 2 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-15 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-15 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-15 | Komatsu 30t Articulated Dumptruck #2 | 9.5 | 1.5 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-15 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-15 | Service Truck | 0.8 | 10.2 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-15 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-15 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-15 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-15 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-15 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-16 | Operator 1 | 9.5 | 0 | 0
2025-11-16 | Operator 2 | 9.5 | 0 | 0
2025-11-16 | Operator 3 | 9.5 | 0 | 0
2025-11-16 | Operator 4 | 9.5 | 0 | 0
2025-11-16 | Operator 5 | 9.5 | 0 | 0
2025-11-16 | Operator 6 | 9.5 | 0 | 0
2025-11-16 | D6 Dozer LGP Tracks | 0.1 | 10.9 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-16 | 25t Excavator LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Benthic Drying Trial
2025-11-16 | 36t Excavator LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-16 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-16 | Komatsu 30t Articulated Dumptruck #2 | 0.5 | 10.5 | 0 | 0 | [8 empty] | Load, Haul & Place Benthic Trial Access Road
2025-11-16 | Rigid Watercart | 1 | 10 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-16 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Plant Maintenance
2025-11-16 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-16 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-16 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-16 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-16 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-17 | Operator 1 | 0 | 0 | 0
2025-11-17 | Operator 2 | 0 | 0 | 0
2025-11-17 | Operator 3 | 0 | 0 | 0
2025-11-17 | Operator 4 | 0 | 0 | 0
2025-11-17 | Operator 5 | 0 | 0 | 0
2025-11-17 | Operator 6 | 0 | 0 | 0
2025-11-17 | D6 Dozer LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | 25t Excavator LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | 36t Excavator LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Fly out day
2025-11-17 | Komatsu 30t Articulated Dumptruck #2 | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | Rigid Watercart | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Fly out day
2025-11-17 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-17 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-17 | RE 4WD Twin Cab LV #1 | 0 | 0 | 0 | 0
2025-11-17 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 7 | [8 empty] | Pumps on site
2025-11-17 | 4" Transfer Pump | 0 | 0 | 0 | 7 | [8 empty] | Pumps on site
2025-11-24 | Operator 1 | 10 | 0 | 0
2025-11-24 | Operator 2 | 10 | 0 | 0
2025-11-24 | Operator 3 | 10 | 0 | 0
2025-11-24 | Operator 4 | 10 | 0 | 0
2025-11-24 | Operator 5 | 10 | 0 | 0
2025-11-24 | Operator 6 | 10 | 0 | 0
2025-11-24 | Supervisor | 10 | 0 | 0
2025-11-24 | D6 Dozer LGP Tracks | 0.3 | 0.7 | 0 | 0 | [8 empty] | Levee works
2025-11-24 | 25t Excavator LGP Tracks | 4 | 6 | 0 | 0 | [8 empty] | Pond 6
2025-11-24 | 36t Excavator LGP Tracks | 2 | 8 | 0 | 0 | [8 empty] | Pump pad
2025-11-24 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 10 | 0 | [8 empty] | Breakdown
2025-11-24 | Komatsu 30t Articulated Dumptruck #2 | 3.5 | 6.5 | 0 | 0 | [8 empty] | Haulage
2025-11-24 | Rigid Watercart | 5 | 5 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-24 | Service Truck | 0 | 10 | 0 | 0 | [8 empty] | Standby
2025-11-24 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-24 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-24 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-24 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-24 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-25 | Operator 1 | 11.5 | 0 | 0
2025-11-25 | Operator 2 | 11.5 | 0 | 0
2025-11-25 | Operator 3 | 11.5 | 0 | 0
2025-11-25 | Operator 4 | 11.5 | 0 | 0
2025-11-25 | Operator 5 | 11.5 | 0 | 0
2025-11-25 | Operator 6 | 11.5 | 0 | 0
2025-11-25 | Supervisor | 11.5 | 0 | 0
2025-11-25 | D6 Dozer LGP Tracks | 1.3 | 9.7 | 0 | 0 | [8 empty] | Levee works
2025-11-25 | 25t Excavator LGP Tracks | 6 | 5 | 0 | 0 | [8 empty] | Pond 6
2025-11-25 | 36t Excavator LGP Tracks | 9 | 2 | 0 | 0 | [8 empty] | Pump pad
2025-11-25 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-25 | Komatsu 30t Articulated Dumptruck #2 | 6.5 | 4.5 | 0 | 0 | [8 empty] | Haulage
2025-11-25 | Rigid Watercart | 8 | 3 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-25 | Service Truck | 0.8 | 10.2 | 0 | 0 | [8 empty] | Refuelling machines
2025-11-25 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-25 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-25 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-25 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-25 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-26 | Operator 1 | 11.5 | 0 | 0
2025-11-26 | Operator 2 | 11.5 | 0 | 0
2025-11-26 | Operator 3 | 11.5 | 0 | 0
2025-11-26 | Operator 4 | 11.5 | 0 | 0
2025-11-26 | Operator 5 | 11.5 | 0 | 0
2025-11-26 | Operator 6 | 11.5 | 0 | 0
2025-11-26 | Supervisor | 11.5 | 0 | 0
2025-11-26 | D6 Dozer LGP Tracks | 3.5 | 7.5 | 0 | 0 | [8 empty] | Levee works
2025-11-26 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Pond 6
2025-11-26 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Pump pad
2025-11-26 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-26 | Komatsu 30t Articulated Dumptruck #2 | 7 | 4 | 0 | 0 | [8 empty] | Haulage
2025-11-26 | Rigid Watercart | 10 | 1 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-26 | Service Truck | 0.3 | 10.7 | 0 | 0 | [8 empty] | Refuelling machines
2025-11-26 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-26 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-26 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-26 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-26 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-27 | Operator 1 | 11.5 | 0 | 0
2025-11-27 | Operator 2 | 11.5 | 0 | 0
2025-11-27 | Operator 3 | 11.5 | 0 | 0
2025-11-27 | Operator 4 | 11.5 | 0 | 0
2025-11-27 | Operator 5 | 11.5 | 0 | 0
2025-11-27 | Operator 6 | 11.5 | 0 | 0
2025-11-27 | Supervisor | 11.5 | 0 | 0
2025-11-27 | D6 Dozer LGP Tracks | 7.2 | 3.8 | 0 | 0 | [8 empty] | Benthic access road
2025-11-27 | 25t Excavator LGP Tracks | 10 | 1 | 0 | 0 | [8 empty] | Mixing and loading Pond 6 Stock pile
2025-11-27 | 36t Excavator LGP Tracks | 8 | 3 | 0 | 0 | [8 empty] | Pump pad
2025-11-27 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-27 | Komatsu 30t Articulated Dumptruck #2 | 8.5 | 2.5 | 0 | 0 | [8 empty] | Haulage
2025-11-27 | Rigid Watercart | 9 | 2 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-27 | Service Truck | 0.5 | 10.5 | 0 | 0 | [8 empty] | Refuelling machines
2025-11-27 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-27 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-27 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-27 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-27 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-28 | Operator 1 | 11.5 | 0 | 0
2025-11-28 | Operator 2 | 11.5 | 0 | 0
2025-11-28 | Operator 3 | 11.5 | 0 | 0
2025-11-28 | Operator 4 | 11.5 | 0 | 0
2025-11-28 | Operator 5 | 11.5 | 0 | 0
2025-11-28 | Operator 6 | 11.5 | 0 | 0
2025-11-28 | Supervisor | 11.5 | 0 | 0
2025-11-28 | D6 Dozer LGP Tracks | 5 | 6 | 0 | 0 | [8 empty] | Benthic access road/ Tip head
2025-11-28 | 25t Excavator LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Mixing and loading Pond 6 Stock pile
2025-11-28 | 36t Excavator LGP Tracks | 5 | 6 | 0 | 0 | [8 empty] | Pump pad Pond 6/ Pump install
2025-11-28 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-28 | Komatsu 30t Articulated Dumptruck #2 | 2.8 | 8.2 | 0 | 0 | [8 empty] | Haulage / Down tyre damage
2025-11-28 | Rigid Watercart | 6 | 5 | 0 | 0 | [8 empty] | Dust Suppression
2025-11-28 | Service Truck | 0 | 11 | 0 | 0 | [8 empty] | Did not use
2025-11-28 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-28 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-28 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-28 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-28 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-29 | Operator 1 | 11.5 | 0 | 0
2025-11-29 | Operator 2 | 11.5 | 0 | 0
2025-11-29 | Operator 3 | 11.5 | 0 | 0
2025-11-29 | Operator 4 | 11.5 | 0 | 0
2025-11-29 | Operator 5 | 11.5 | 0 | 0
2025-11-29 | Operator 6 | 11.5 | 0 | 0
2025-11-29 | Supervisor | 11.5 | 0 | 0
2025-11-29 | D6 Dozer LGP Tracks | 4.1 | 6.9 | 0 | 0 | [8 empty] | Borrows works
2025-11-29 | 25t Excavator LGP Tracks | 6 | 5 | 0 | 0 | [8 empty] | Access Rd pipe drainage
2025-11-29 | 36t Excavator LGP Tracks | 3 | 8 | 0 | 0 | [8 empty] | Dewatering/ Pipe in ground for drainage
2025-11-29 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-29 | Komatsu 30t Articulated Dumptruck #2 | 0 | 0 | 11 | 0 | [8 empty] | Down tyre damage
2025-11-29 | Rigid Watercart | 3 | 8 | 0 | 0 | [8 empty] | Dust Suppression Pond 6
2025-11-29 | Service Truck | 1.5 | 9.5 | 0 | 0 | [8 empty] | Refuelling
2025-11-29 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-29 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-29 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-29 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-29 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-11-30 | Operator 1 | 11.5 | 0 | 0
2025-11-30 | Operator 2 | 11.5 | 0 | 0
2025-11-30 | Operator 3 | 11.5 | 0 | 0
2025-11-30 | Operator 4 | 11.5 | 0 | 0
2025-11-30 | Operator 5 | 11.5 | 0 | 0
2025-11-30 | Operator 6 | 11.5 | 0 | 0
2025-11-30 | Supervisor | 11.5 | 0 | 0
2025-11-30 | D6 Dozer LGP Tracks | 7 | 4 | 0 | 0 | [8 empty] | Borrow Pit 5 works/ drainage
2025-11-30 | 25t Excavator LGP Tracks | 6 | 5 | 0 | 0 | [8 empty] | Draing access Rd
2025-11-30 | 36t Excavator LGP Tracks | 4 | 7 | 0 | 0 | [8 empty] | Dewatering/ Pipe in ground for drainage
2025-11-30 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-11-30 | Komatsu 30t Articulated Dumptruck #2 | 0 | 0 | 11 | 0 | [8 empty] | Down tyre damage
2025-11-30 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Dust Suppression Pond 6
2025-11-30 | Service Truck | 8.4 | 0 | 2.6 | 0 | [8 empty] | Refuelling/ Down for air hose to fuel
2025-11-30 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-30 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-11-30 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-11-30 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-11-30 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-12-01 | Operator 1 | 11.5 | 0 | 0
2025-12-01 | Operator 2 | 11.5 | 0 | 0
2025-12-01 | Operator 3 | 11.5 | 0 | 0
2025-12-01 | Operator 4 | 11.5 | 0 | 0
2025-12-01 | Operator 5 | 11.5 | 0 | 0
2025-12-01 | Operator 6 | 11.5 | 0 | 0
2025-12-01 | Supervisor | 11.5 | 0 | 0
2025-12-01 | D6 Dozer LGP Tracks | 3.8 | 7.2 | 0 | 0 | [8 empty] | Borrow Pit 5 works/ drainage
2025-12-01 | 25t Excavator LGP Tracks | 2 | 9 | 0 | 0 | [8 empty] | Draing access Rd
2025-12-01 | 36t Excavator LGP Tracks | 2 | 9 | 0 | 0 | [8 empty] | Dewatering/ Pipe in ground for drainage
2025-12-01 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-12-01 | Komatsu 30t Articulated Dumptruck #2 | 0 | 0 | 11 | 0 | [8 empty] | Down tyre damage
2025-12-01 | Rigid Watercart | 3 | 8 | 0 | 0 | [8 empty] | Dust Suppression Pond 6
2025-12-01 | Service Truck | 2.6 | 8.4 | 0 | 0 | [8 empty] | Refuelling
2025-12-01 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-01 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-12-01 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-01 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-12-01 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-12-02 | Operator 1 | 10 | 0 | 0
2025-12-02 | Operator 2 | 10 | 0 | 0
2025-12-02 | Operator 3 | 10 | 0 | 0
2025-12-02 | Operator 4 | 10 | 0 | 0
2025-12-02 | Operator 5 | 10 | 0 | 0
2025-12-02 | Operator 6 | 10 | 0 | 0
2025-12-02 | Supervisor | 11.5 | 0 | 0
2025-12-02 | D6 Dozer LGP Tracks | 8.4 | 2.6 | 0 | 0 | [8 empty] | Borrow Pit 5 works/ drainage
2025-12-02 | 25t Excavator LGP Tracks | 0 | 11 | 0 | 0 | [8 empty] | Down due to E-Stop Damage Caused from the task.
2025-12-02 | 36t Excavator LGP Tracks | 4 | 7 | 0 | 0 | [8 empty] | Dewatering/ Pipe in ground for drainage
2025-12-02 | Bell 30t Articulated Dumptruck #1 | 0 | 0 | 11 | 0 | [8 empty] | Breakdown
2025-12-02 | Komatsu 30t Articulated Dumptruck #2 | 0 | 0 | 11 | 0 | [8 empty] | Down tyre damage
2025-12-02 | Rigid Watercart | 7 | 4 | 0 | 0 | [8 empty] | Dust Suppression Pond 6
2025-12-02 | Service Truck | 3.5 | 3.5 | 4 | 0 | [8 empty] | Refuelling
2025-12-02 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-02 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-12-02 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-02 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-12-02 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-12-03 | Operator 1 | 10 | 0 | 0
2025-12-03 | Operator 2 | 10 | 0 | 0
2025-12-03 | Operator 3 | 10 | 0 | 0
2025-12-03 | Operator 4 | 10 | 0 | 0
2025-12-03 | Operator 5 | 10 | 0 | 0
2025-12-03 | Operator 6 | 10 | 0 | 0
2025-12-03 | Supervisor | 11.5 | 0 | 0
2025-12-03 | D6 Dozer LGP Tracks | 1.8 | 8.2 | 0 | 0 | [8 empty] | Borrow Pit 5 works/ drainage
2025-12-03 | 25t Excavator LGP Tracks | 0 | 10 | 10 | 0 | [8 empty] | Down due to E-Stop Damage Caused from the task.
2025-12-03 | 36t Excavator LGP Tracks | 5 | 5 | 0 | 0 | [8 empty] | Benthic Turning over
2025-12-03 | Bell 30t Articulated Dumptruck #1 | 0 | 10 | 10 | 0 | [8 empty] | Breakdown
2025-12-03 | Komatsu 30t Articulated Dumptruck #2 | 0 | 10 | 10 | 0 | [8 empty] | Down tyre damage
2025-12-03 | Rigid Watercart | 5 | 5 | 0 | 0 | [8 empty] | Dust Suppression Pond 6/ Watering Pond 5 Hydromulch
2025-12-03 | Service Truck | 4.3 | 5.7 | 0 | 0 | [8 empty] | Refuelling
2025-12-03 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-03 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-12-03 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-03 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-12-03 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-12-04 | Operator 1 | 10 | 0 | 0
2025-12-04 | Operator 2 | 10 | 0 | 0
2025-12-04 | Operator 3 | 10 | 0 | 0
2025-12-04 | Operator 4 | 10 | 0 | 0
2025-12-04 | Operator 5 | 10 | 0 | 0
2025-12-04 | Operator 6 | 10 | 0 | 0
2025-12-04 | Supervisor | 11.5 | 0 | 0
2025-12-04 | D6 Dozer LGP Tracks | 7.1 | 2.9 | 0 | 0 | [8 empty] | Borrow Pit 5 works/ drainage
2025-12-04 | 25t Excavator LGP Tracks | 0 | 10 | 10 | 0 | [8 empty] | Down due to E-Stop Damage Caused from the task.
2025-12-04 | 36t Excavator LGP Tracks | 7 | 3 | 0 | 0 | [8 empty] | Benthic Turning over
2025-12-04 | Bell 30t Articulated Dumptruck #1 | 0 | 10 | 10 | 0 | [8 empty] | Breakdown
2025-12-04 | Komatsu 30t Articulated Dumptruck #2 | 0 | 10 | 10 | 0 | [8 empty] | Down tyre damage
2025-12-04 | Rigid Watercart | 4 | 6 | 0 | 0 | [8 empty] | Dust Suppression Pond 6/ Watering Pond 5 Hydromulch
2025-12-04 | Service Truck | 5.7 | 4.3 | 0 | 0 | [8 empty] | Refuelling
2025-12-04 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-04 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-12-04 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-04 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-12-04 | 4" Transfer Pump | 0 | 0 | 0 | 1
2025-12-06 | Operator 1 | 10 | 0 | 0
2025-12-06 | Operator 2 | 10 | 0 | 0
2025-12-06 | Operator 3 | 10 | 0 | 0
2025-12-06 | Operator 4 | 10 | 0 | 0
2025-12-06 | Operator 5 | 10 | 0 | 0
2025-12-06 | Operator 6 | 10 | 0 | 0
2025-12-06 | Supervisor | 11.5 | 0 | 0
2025-12-06 | D6 Dozer LGP Tracks | 0 | 10 | 0 | 0 | [8 empty] | Standby due to weather
2025-12-06 | 25t Excavator LGP Tracks | 0 | 10 | 0 | 0 | [8 empty] | Standby due to weather
2025-12-06 | 36t Excavator LGP Tracks | 0 | 10 | 0 | 0 | [8 empty] | Standby due to weather
2025-12-06 | Bell 30t Articulated Dumptruck #1 | 0 | 10 | 10 | 0 | [8 empty] | Breakdown
2025-12-06 | Komatsu 30t Articulated Dumptruck #2 | 0 | 10 | 10 | 0 | [8 empty] | Down tyre damage
2025-12-06 | Rigid Watercart | 0 | 10 | 0 | 0 | [8 empty] | Down tyre damage
2025-12-06 | Service Truck | 0 | 10 | 0 | 0 | [8 empty] | Standby due to weather
2025-12-06 | 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-06 | 4WD Twin Cab LV #2 | 11 | 0 | 0 | 0
2025-12-06 | RE 4WD Twin Cab LV #1 | 11 | 0 | 0 | 0
2025-12-06 | 3" Flex Drive Trash Pump | 0 | 0 | 0 | 1
2025-12-06 | 4" Transfer Pump | 0 | 0 | 0 | 1

## RE Rates
Equipment | Plant Rate (/hr) | Variations Rate/Day | Operator Rate (/hr) | Standby Rate (/hr) | Prep & Onboard | Mob Barge | DeMob Barge | Mob Road | DeMob Road | Operator Induction | Operator Mob | Operator DeMob | GST %
25t Excavator LGP Tracks | 139.15 |  |  | 83.6 | 22584.65 | 6790.85 | 6790.85 | 48809.2 | 48809.2 |  |  |  | 10
36t Excavator LGP Tracks | 168.3 |  |  | 101.2 | 26039.75 | 8044.85 | 8044.85 | 52336.9 | 52336.9 |  |  |  | 10
D6 Dozer LGP Tracks | 255.75 |  |  | 153.45 | 8505.75 | 13294.6 | 13294.6 | 39006.55 | 39006.55 |  |  |  | 10
Bell 30t Articulated Dumptruck #1 | 179.3 |  |  | 107.8 | 8505.75 | 10552.3 | 10552.3 | 25306.05 | 25306.05 |  |  |  | 10
Komatsu 30t Articulated Dumptruck #2 | 179.3 |  |  | 107.8 | 8505.75 | 10552.3 | 10552.3 | 25306.05 | 25306.05 |  |  |  | 10
Service Truck | 173.8 |  |  | 104.5 | 13297.9 | 6386.05 | 6386.05 | 22669.35 | 22669.35 |  |  |  | 10
Rigid Watercart | 112.75 |  |  | 67.65 | 5988.95 | 4819.1 | 4819.1 | 21885.6 | 21885.6 |  | 0 | 0 | 10
4WD Twin Cab LV #1 | 29.15 |  |  | 17.6 | 4601.3 | 1684.65 | 1684.65 | 5223.25 | 5223.25 |  | 0 | 0 | 10
4WD Twin Cab LV #2 | 29.15 |  |  | 17.6 | 4601.3 | 1684.65 | 1684.65 | 5223.25 | 5223.25 |  | 0 | 0 | 10
RE 4WD Twin Cab LV #1 | 29.15 |  |  | 17.6 | 4601.3 | 1684.65 | [6 empty] | 10
RE 4WD Twin Cab LV #2 | 29.15 |  |  | 17.6 | [8 empty] | 10
Operator 1 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 2 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 3 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 4 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 5 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 6 |  |  | 115.5 | 115.5 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
Operator 7 |  |  | 115.5 | 0 | [8 empty] | 10
Supervisor |  |  | 142 | 142 | [5 empty] | 1750.65 | 575.3 | 345.4 | 10
3" Flex Drive Trash Pump |  | 312.4 | [10 empty] | 10
4" Transfer Pump |  | 187 | [10 empty] | 10
Wallaby Beach Accommodation |  | 2316.3504 | [10 empty] | 10
Wallaby Beach Camp |  | 0 | [10 empty] | 10

## Site Instructions & Variations
Date | SI# | Description | Cost
2025-11-30 | Wallaby Beach Accommodation | Wallaby Beach Accommodation | 2316.3504

## Operators
Real Name | Operator Code (e.g. Operator 1)
25t Excavator | 25t Excavator LGP Tracks
36t Excavator | 36t Excavator LGP Tracks
Jarrad Ernst | Supervisor
Arthur De Saint Andrieu | Operator 3
Bell Moxy. TAT 56 | Bell 30t Articulated Dumptruck #1
Byron McCann | Operator 2
D6 Dozer | D6 Dozer LGP Tracks
First operational shift
Jack Barlee | Operator 5
Komatsu Moxy. TAT 52 | Komatsu 30t Articulated Dumptruck #2
Materials Delivered / used:
Materials Delivered/ used:
Payden Coghill | Operator 4
Plant
Progress/ Notes:
Service Truck | Service Truck
Steven Mungatopi | Operator 1
Stewart Rioli | Operator 6
Water Truck | Rigid Watercart
4WD Twin Cab LV #1 | 4WD Twin Cab LV #1
4WD Twin Cab LV #2 | 4WD Twin Cab LV #2
RE 4WD Twin Cab LV #1 | RE 4WD Twin Cab LV #1
3" Flex Drive Trash Pump | 3" Flex Drive Trash Pump
4" Transfer Pump | 4" Transfer Pump